## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Material Requisition To Resource Division |  |  | RTOR000241/2022-2023 | 2726/TD | 06/02/2023 | 06/02/2023 | Resource Division | 59.37 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BETULYA CHAKLALPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001323/2022-2023 | 2325/W/MMD | 29/12/2022 | 27/06/2023 | S.S.GHORAI | 23.7 | 14.81 | 62.47 | 55
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Betula Chaklalpur Water Supply Scheme at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001276/2023-2024 | 1050/TD | 15/03/2024 | 25/03/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 94/TD | 05/01/2024 | 05/01/2024 | Resource Division | 12.25 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Quotation Bill for New Service connection at T/W NO-I Of BETULIACHAKLALPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818516/QUOT/03 DT. 12-07-2024 Application NO- 2004818516 Application type-New connection Consumer Id- 204355509 |  |  | BILL/01891/2024-2025 | C082410083941 | 08/08/2024 | 08/08/2024 | WBSEDCL | 13.02 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BETULYA CHAKLALPUR PWSS & ADJOINING MOUZAS | SM/12134 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1988 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BETULYA CHAKLAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000206/2023-2024 | 413/TD | 02/05/2023 | 29/04/2025 | DAS CONSTRUCTION | 517.7 | 0 | 0 | 7
Total | [13 empty] | 626.99 | 15.76 | 2.51