## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 2439/TD | 16/01/2023 | 16/01/2023 | Resource Division | 27.79 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Quotation Bill for New Service connection at T/W NO-I Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609871/QUOT/03 DT. 21-02-2024 Application NO- 2004609871 Application type-New connection Reference Id- 204223251 |  |  | BILL/04392/2023-2024 | BP-2023-24-821 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.13 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Quotation Bill for New Service connection at T/W NO-II Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775287/QUOT/03 DT. 14-06-2024 Application NO- 2004775287 MEMO NO: AMR/PHE/176 DT.14/06/2024 Application type-New connection Consumer Id- 204330587 |  |  | BILL/01332/2024-2025 | BP-2024-25-354 | 01/07/2024 | 01/07/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAIPUR and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001317/2022-2023 | 2319/W/MMD | 29/12/2022 | 01/04/2025 | SOUMEN ELECTRIC | 22.78 | 16.14 | 70.85 | 90
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 1632/TD | 18/06/2025 | 18/06/2025 | Resource Division | 9.7 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | NAIPUR & ADJOINING MOUZAS | SM/12135 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 150.73 | 0.77 | 51
Total | [13 empty] | 19635.63 | 166.87 | 0.85