## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALABERIA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001338/2022-2023 | 2343/W/MMD | 29/12/2022 | 27/06/2023 | ORIENTAL ENGINEERING CO. | 25.24 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 2384/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.89 | 0 | 0 | 0
Total | [13 empty] | 45.13 | 0 | 0