## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALABERIA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001338/2022-2023 | 2343/W/MMD | 29/12/2022 | 27/06/2023 | ORIENTAL ENGINEERING CO. | 25.24 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 2384/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.89 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1959 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KALABERIA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000850/2023-2024 | 73/TD | 05/01/2024 | 30/05/2026 | SRIMANTA KUMAR MAITY | 584.3 | 43.7 | 7.48 | 15
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KALABERIA & ADJOINING MOUZAS | SM/12136 | New | Quotation Bill for New Service connection at T/W NO-I Of KALABERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL C.C.C. : BHAGWANPUR C.C.C. Ref. Memo No- 2005232856/QUOT/03 DT. 21-05-2025 Application NO- 2005232856 Application type-New connection CONSUMER ID: 204628888 |  |  | BILL/01391/2025-2026 |  | 12/06/2025 | 12/06/2025 | WBSEDCL | 6.87 | 0 | 0 | 0
Total | [13 empty] | 636.3 | 43.7 | 6.87