## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Material Requisition To Resource Division |  |  | RTOR000303/2022-2023 | 3002/TD | 27/02/2023 | 27/02/2023 | Resource Division | 19.42 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Laying distribution pipe line, Pump House , Boundary Wall, Rising Main & Accommodate FHTC (400 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000885/2022-2023 | 3242/TD | 15/03/2023 | 01/12/2025 | S.D. CONSTRUCTION | 70.03 | 0 | 0 | 70
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd. T/W site at Jamitta Water Supply scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001194/2023-2024 | 829/TD | 05/03/2024 | 29/03/2024 | S.D. CONSTRUCTION | 4.77 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 123/TD | 05/01/2024 | 05/01/2024 | Resource Division | 7.16 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Quotation Bill for New connection Jamitya water supply scheme Tube Well-II. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662461 Ref no.-204260852 |  |  | BILL/00254/2024-2025 | BP-2024-25-27 | 15/04/2024 | 15/04/2024 | WBSEDCL | 10.19 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | New service connection at Jamitya water supply scheme H/W site Kolaghat CCC Block- Kolaghat Application No.-2004803550 Consumer ID.-204346513 Date.-02-07-2024 |  |  | BILL/01469/2024-2025 | BP-2024-25-416 | 15/07/2024 | 15/07/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (653 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000884/2022-2023 | 3241/TD | 15/03/2023 | 01/12/2025 | S.D. CONSTRUCTION | 70.26 | 0 | 0 | 80
8 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Soil investigation & construction of 200 cum OHR (Intze type with pile foundation) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-E) | Assistant Engineer | Junior Engineer | ORD/000892/2022-2023 | 3394/TD | 24/03/2023 | 31/12/2025 | TAPAS SANTRA | 99.27 | 0 | 0 | 70
9 | PURBA MEDINIPUR | Sahid Matangini | Central Drilling | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | PURBA MEDINIPUR | Sahid Matangini | Central Drilling | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Hiring of Diesel Driven Motor cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000008/2024-2025 | 139/S&WSD | 26/06/2024 | 25/12/2024 | ASHUTOSH DAS & CO | 0.86 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | JAMITTA & ADJOINING MOUZAS | SM/12137 | New | Laying distribution pipe line & Accommodate FHTC (110 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 3243/TD | 15/03/2023 | 01/12/2025 | MISHRA ENTERPRISE | 9.53 | 0 | 0 | 100
Total | [13 empty] | 21635.04 | 0 | 0