## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 2472/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.44 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 3081/TD | 28/02/2023 | 20/03/2023 | HYDROTECH ASSOCIATES | 10.01 | 8.28 | 82.77 | 85
3 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 511/TD | 11/05/2023 | 10/06/2023 | MANAS KUMAR SAHA | 93.6 | 57.08 | 60.98 | 30
4 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (300 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 583/TD | 16/05/2023 | 08/02/2025 | RAJ KUMAR SINGHA | 172.52 | 34.27 | 19.87 | 22
5 | PURBA MEDINIPUR | Sutahata | Central Drilling | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Erekhali W/S Scheme (T/W-I & II) , Sutahata Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000121/2023-2024 | 1388/CDD | 19/09/2023 | 14/06/2024 | MENAKA ENTERPRISE | 31.41 | 29.24 | 93.1 | 100
6 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 638/W | 20/02/2024 | 20/02/2024 | Resource Division | 10.55 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Quotation bill for new service connection at TW-II Of Erekhali w/s scheme, Block-Sutahata in the Dist. of purba medinipur under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004923436 Application Type-New Connection Reference ID-204414482 Quotation Date-01/10/2024 Quotation Due Date-01/10/2025 Contract Demand-8344W |  |  | BILL/02676/2024-2025 | C102415718521 | 05/10/2024 | 05/10/2024 | WBSEDCL | 6.17 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Quotation bill for new service connection at TW-I of Eriakhali w/s scheme,Block-Sutahata under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695183 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-8500W |  |  | BILL/00649/2024-2025 | BP-2024-25-108 | 06/05/2024 | 06/05/2024 | WBSEDCL | 6.26 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for EREKHALI and ADJOINING MOUJAS, Block Sutahata, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001325/2022-2023 | 2327/W/MMD | 29/12/2022 | 31/08/2025 | M/S. SAJAHAN CHOWDHURY | 23.69 | 15.21 | 64.19 | 60
10 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000811/2022-2023 | 3080/TD | 28/02/2023 | 07/12/2024 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.86 | 8.05 | 81.7 | 100
11 | PURBA MEDINIPUR | Sutahata | Tamluk Division | EREKHALI AND ADJOINING MOUJAS PWSS | SM/12139 | New | Box Culvert at HW site & 2nd TW site ,Canal crossing & Approach Road of ground water based Erekhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000735/2023-2024 | 2987/TD | 29/11/2023 | 27/03/2025 | A. R. CONSTRUCTION | 18 | 11.6 | 64.42 | 70
Total | [13 empty] | 400.51 | 163.73 | 40.88