## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/12140 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001332/2022-2023 | 2337/W/MMD | 29/12/2022 | 01/12/2025 | DEY ENTERPRISE | 23.7 | 11.09 | 46.78 | 65
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/12140 | New | Material Requisition To Resource Division |  |  | RTOR000212/2022-2023 | 2467/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.42 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/12140 | New | Electric Quotation for RAMCHANDRAPUR Water Supply Scheme , (Ref. ID-204075844) |  |  | BILL/02185/2023-2024 | BP-2023-24-239 | 12/09/2023 | 12/09/2023 | WBSEDCL | 3.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/12140 | New | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 114/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.32 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/12140 | New | Quotation Bill For Ramchandrapur W/S Scheme T/W-II Kolaghat CCC Application No=2005024015 Reference ID=204482671 |  |  | BILL/03943/2024-2025 | C012539022843 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.36 | 0 | 0 | 0
Total | [13 empty] | 61.75 | 11.09 | 17.95