## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12141 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MALIKPUR and ADJOINING MOUJAS, Block Potashpur II District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001327/2022-2023 | 2329/W/MMD | 29/12/2022 | 27/06/2023 | DAS ENTERPRISE | 23.64 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12141 | New | Material Requisition To Resource Division |  |  | RTOR000198/2022-2023 | 2454/TD | 16/01/2023 | 16/01/2023 | Resource Division | 39.75 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12141 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 1658/TD | 29/04/2024 | 29/04/2024 | Resource Division | 14.83 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | MALIKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12141 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 26/02/2026 | S & P ENTERPRISE | 1928.99 | 0 | 0 | 30
Total | [13 empty] | 2007.21 | 0 | 0