## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 3105/TD | 02/03/2023 | 17/03/2023 | DEBDUT CONSTRUCTION | 16.69 | 0 | 0 | 68
2 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000827/2022-2023 | 3120/TD | 02/03/2023 | 22/03/2023 | TAPAN BERA | 20.42 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 2471/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.07 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARIBALLABHPUR and ADJOINING MOUJAS, Block Sutahata District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001328/2022-2023 | 2330/W/MMD | 29/12/2022 | 27/06/2023 | MAHADEV ENTERPRISE | 23.65 | 0 | 0 | 80
5 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (25 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 3104/TD | 02/03/2023 | 02/02/2026 | MODERN CONSTRUCTION | 10.75 | 0 | 0 | 36
6 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Construction of R.C.C. approach road at Head work site of Hariballabhpur & its adjoining mouzas Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte.(Length of Approach Road-45mtr) | Assistant Engineer |  | ORD/000863/2023-2024 | 240/TD | 11/01/2024 | 31/01/2024 | G. S. CONSTRUCTION | 4.78 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000896/2022-2023 | 3346/TD | 22/03/2023 | 16/04/2023 | PRANTIK DRILLING AGENCY | 30.88 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 504/TD | 11/05/2023 | 25/12/2024 | TAPAN BERA | 20.43 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 637/W | 20/02/2024 | 20/02/2024 | Resource Division | 10.66 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Quotation Bill for New Service Connection at PH-II of Hariballavpur pwss,Block-Sutahata, under MMD,PHE Dte. Name of C.C.C.- Chaitanyapur Application no.-2004644794 Application Type-New Connection Quotation Date-15/03/2024 Quotation Due Date-17/03/2025 |  |  | BILL/04750/2023-2024 | BP-2023-24-920 | 28/03/2024 | 28/03/2024 | WBSEDCL | 0.28 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Quotation Bill for new service connection at TW-I & II of Hariballavpur w/s scheme under MMD,PHE, Dte. Block-Sutahata,Chaitanyapur C.C.C Memo No.-2004632082/Quot/03 Date-05/03/2024 Application No.-2004632082 Application Type-New Connection Reference ID-204237950 |  |  | BILL/04382/2023-2024 | BP-2023-24-826 | 13/03/2024 | 13/03/2024 | WBSEDCL | 13.11 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 3103/TD | 02/03/2023 | 26/10/2024 | MUKHERJEE ENTERPRISE | 19.22 | 0 | 0 | 26
13 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (725nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer | Junior Engineer | ORD/000069/2023-2024 | 139/TD | 10/04/2023 | 30/03/2025 | S. B. ASSOCIATES | 83.67 | 0 | 0 | 55
14 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000238/2023-2024 | 499/TD | 11/05/2023 | 01/09/2025 | BARH CONSTRUCTION | 131.4 | 0 | 0 | 70
15 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000816/2022-2023 | 3106/TD | 02/03/2023 | 26/12/2024 | TAPAN BERA | 21.6 | 0 | 0 | 90
16 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer | Junior Engineer | ORD/000817/2022-2023 | 3107/TD | 02/03/2023 | 23/12/2024 | ELECTIVA ENTERPRISE | 4.53 | 0 | 0 | 50
17 | PURBA MEDINIPUR | Sutahata | Tamluk Division | HARIBALLABHPUR AND ADJOINING MOUJAS PWSS | SM/12142 | New | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer | Junior Engineer | ORD/000240/2023-2024 | 503/TD | 11/05/2023 | 21/12/2024 | SUDIP MANNA | 20.62 | 0 | 0 | 75
Total | [13 empty] | 450.76 | 0 | 0