## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS | SM/12143 | New | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 2702/TD | 06/02/2023 | 06/02/2023 | Resource Division | 14.6 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | BALGOBINDAPUR & ADJOINING MOUZAS | SM/12143 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BALGOBINDAPUR and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001329/2022-2023 | 2334/W/MMD | 29/12/2022 | 27/06/2023 | S.S.GHORAI | 23.7 | 0 | 0 | 55
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS | SM/12143 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 1648/TD | 29/04/2024 | 29/04/2024 | Resource Division | 13.17 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | BALGOBINDAPUR & ADJOINING MOUZAS | SM/12143 | New | Quotation Bill for New Service connection at T/W NO-I Of BALGOBINDAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004675882/QUOT/03 DT. 12-04-2024 Application NO- 2004675882 Application type-New connection Consumer Id- 204270815 |  |  | BILL/00578/2024-2025 | BP-2024-25-100 | 26/04/2024 | 26/04/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | BALGOBINDAPUR & ADJOINING MOUZAS | SM/12143 | New | Sinking Tube well,Pump House , Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2138 nos), Including 2 years of operation maintance under JJM with allied work for Balgobindapur- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000613/2023-2024 | 2272/TD | 05/09/2023 | 31/07/2025 | DAS ENTERPRISE | 693.39 | 0 | 0 | 40
Total | [13 empty] | 750.03 | 0 | 0