## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Material Requisition To Resource Division |  |  | RTOR000182/2022-2023 | 2431/TD | 16/01/2023 | 16/01/2023 | Resource Division | 21.73 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001330/2022-2023 | 2335/W/MMD | 29/12/2022 | 27/06/2023 | ORIENTAL ENGINEERING CO. | 23.68 | 21.94 | 92.67 | 80
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Basanta Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000877/2023-2024 | 199/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1560/TD | 23/04/2024 | 23/04/2024 | Resource Division | 12.76 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Quotation for new service connection at Basantachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756260, Ref ID 204319518) |  |  | BILL/01700/2024-2025 | BP-2024-25-492 | 29/07/2024 | 29/07/2024 | WBSEDCL | 5.19 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BASANTA CHAK AND ADJOINING MOUJAS PWSS | SM/12144 | New | Quotation for Basantachak w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608977, Ref ID-204222619) |  |  | BILL/04497/2023-2024 | BP-2023-24-853 | 16/03/2024 | 16/03/2024 | WBSEDCL | 2.96 | 0 | 0 | 0
Total | [13 empty] | 67.27 | 21.94 | 32.62