## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS | SM/12145 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 349/TD | 26/04/2023 | 26/04/2023 | Resource Division | 51.9 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | TANIA BILA AND ADJOINING MOUJAS PWSS | SM/12145 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TANIA BILA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001318/2022-2023 | 2320/W/MMD | 29/12/2022 | 27/06/2023 | M/S. SAJAHAN CHOWDHURY | 22.79 | 0 | 0 | 65
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS | SM/12145 | New | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 1664/TD | 29/04/2024 | 29/04/2024 | Resource Division | 7.61 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TANIA BILA AND ADJOINING MOUJAS PWSS | SM/12145 | New | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 01/12/2025 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 0 | 0 | 60
Total | [13 empty] | 1296.72 | 0 | 0