## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Material Requisition To Resource Division |  |  | RTOR000183/2022-2023 | 2430/TD | 16/01/2023 | 16/01/2023 | Resource Division | 26.3 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKCHA and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001331/2022-2023 | 2336/W/MMD | 29/12/2022 | 27/06/2023 | PRANAB KUMAR DAS | 23.69 | 0 | 0 | 90
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Bakcha PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000879/2023-2024 | 201/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1559/TD | 23/04/2024 | 23/04/2024 | Resource Division | 12.6 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Quotation for new service connection at Bakcha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631507, Ref ID 204237228) |  |  | BILL/04744/2023-2024 | BP-2023-24-906 | 28/03/2024 | 28/03/2024 | WBSEDCL | 6.12 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Quotation for Bakcha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004620130, Ref ID-204229481) |  |  | BILL/04502/2023-2024 | BP-2023-24-854 | 16/03/2024 | 16/03/2024 | WBSEDCL | 2.97 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.01.2025 to 31.06.2025 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000573/2024-2025 | 344/RWS/TSD | 30/12/2024 | 29/06/2025 | SADHAN CHANDRA SAMANTA | 0.86 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | BAKCHA AND ADJOINING MOUJAS PWSS | SM/12146 | New | Installation of display Board at 5 nos { 1. GOBARDAN PWSS( PUMP HOUSE -2) , 2. UTTAR CHONGRA CHAK PWSS( PUMP HOUSE 1 & 2), 3.BAKCHA PWSS( PUMP HOUSE 1 & 2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000253/2025-2026 | 58/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.83 | 0 | 0 | 100
Total | [13 empty] | 74.33 | 0 | 0