## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Central Drilling | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Providing drilling crew and other works for construction of Tube Well (300 mm X 200 mm x 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W-III), Moyna Block under Purba Medinipur Distrct, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000058/2023-2024 | 543/CDD | 02/06/2023 | 02/07/2023 | WIZARDTECH SOLUTION | 17.72 | 15.95 | 89.99 | 100
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Material Requisition To Resource Division |  |  | RTOR000188/2022-2023 | 2429/TD | 16/01/2023 | 16/01/2023 | Resource Division | 23.04 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Laying distribution System & Accommodate FHTC (520 nos) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C,MOUZA-SHRI BRINDABAN CHAK) | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 3215/TD | 14/03/2023 | 01/03/2026 | MAA KALI CONSTRUCTION | 71.8 | 40.8 | 56.82 | 55
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Laying distribution System, Accommodate FHTC (700 Nos) & Construction of Boundary Wall with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B,MOUZA-UTTAMPUR) | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 523/TD | 11/05/2023 | 07/11/2025 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 136.15 | 90.38 | 66.39 | 65
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 350cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000857/2023-2024 | 170/TD | 09/01/2024 | 07/07/2024 | SATYABRATA BHAUMIK | 133.51 | 45.78 | 34.29 | 10
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Earth work in filling by carried earth and Construction of link Road for Ramchandrapur and its adjoining mouzas new Piped Water Supply Scheme at Head Work Site within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001111/2023-2024 | 563/TD | 15/02/2024 | 06/03/2024 | KIRON CONSTRUCTION | 5.66 | 0 | 0 | 11
7 | PURBA MEDINIPUR | Moyna | Central Drilling | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Ramchandrapur W/S Scheme (T/W -II ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000100/2023-2024 | 542/CDD | 02/06/2023 | 10/06/2024 | UNIVERSAL ENTERPRISES | 17.74 | 14.87 | 83.82 | 100
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 1570/TD | 23/04/2024 | 23/04/2024 | Resource Division | 13.75 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Ramchandrapur W/S scheme PH No.-I Application No.-2004543119 Ref.-204175235 |  |  | BILL/03266/2023-2024 | BP-2023-24-512 | 09/01/2024 | 09/01/2024 | WBSEDCL | 2.95 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Laying distribution System, Accommodate FHTC (1012 nos) Construction of Switch Room cum Chlorine Room I & II and Interconnection of Risisng main with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A,MOUZA-RAMCHANDRAPUR) | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 498/TD | 11/05/2023 | 25/08/2025 | S.K. MONDAL | 138.29 | 78.3 | 56.62 | 80
11 | PURBA MEDINIPUR | Moyna | Tamluk Division | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Retaining wall cum guard wall , Approach road, Earth filling at 2nd Tube Site under Ramchandrapur and Its adjoing Mouzas PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Division PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000903/2023-2024 | 245/TD | 11/01/2024 | 19/12/2024 | ANIRBAN MONDAL | 6.79 | 5.34 | 78.7 | 25
12 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001326/2022-2023 | 2328/W/MMD | 29/12/2022 | 30/04/2025 | SOUMEN ELECTRIC | 23.68 | 20.23 | 85.46 | 85
13 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | RAMCHANDRAPUR AND ADJOINING MOUJAS | SM/12147 | New | New service connetion at Ramchandrapur PH II in the district of Purba Medinipur under MMD PHE Dte. (App No: 2004962417, Con ID 204443611) |  |  | BILL/03274/2024-2025 | C122406882987 | 06/12/2024 | 06/12/2024 | WBSEDCL | 8.89 | 0 | 0 | 0
Total | [13 empty] | 599.97 | 311.66 | 51.95