## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Brindabanpur W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000110/2023-2024 | 1395/CDD | 19/09/2023 | 19/10/2023 | MENAKA ENTERPRISE | 28.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | Material Requisition To Resource Division |  |  | RTOR000308/2022-2023 | 2965/TD | 27/02/2023 | 27/02/2023 | Resource Division | 23.38 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BRINDABANPUR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001316/2022-2023 | 2318/W/MMD | 29/12/2022 | 27/06/2023 | AHALYA ENGINEERING WORKS | 21.61 | 19.67 | 91 | 75
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 630/W | 20/02/2024 | 20/02/2024 | Resource Division | 6.3 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | BRINDABANPUR w/s SCHEME PH.-I APPLICATION NO.-2004567517 |  |  | BILL/03536/2023-2024 | BP-2023-24-610 | 07/02/2024 | 07/02/2024 | WBSEDCL | 5.95 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BRINDABANPUR & ADJOINING MOUJAS PWSS | SM/12148 | New | BRINDABANPUR w/s SCHEME PH.-II APPLICATION NO.-2004570658 |  |  | BILL/03537/2023-2024 | BP-2023-24-609 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
Total | [13 empty] | 89.92 | 19.67 | 21.87