## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GOBINDAPUR & ADJOINING MOUZAS | SM/12149 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - IV at GOBINDAPUR Zone-II Water supply scheme,Block : Shahid Matangini, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001176/2023-2024 | 2612/W/MMD | 19/09/2023 | 17/03/2024 | PURUSHOTTAM ENTERPRISE | 13.17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GOBINDAPUR & ADJOINING MOUZAS | SM/12149 | New | Material Requisition To Resource Division |  |  | RTOR000278/2022-2023 | 2682/TD | 06/02/2023 | 06/02/2023 | Resource Division | 14.87 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | GOBINDAPUR & ADJOINING MOUZAS | SM/12149 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOBINDAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002197/2022-2023 | 454/W/MMD | 20/03/2023 | 10/09/2024 | S.S.ENTERPRISES | 21.62 | 0 | 0 | 20
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | GOBINDAPUR & ADJOINING MOUZAS | SM/12149 | New | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 104/TD | 05/01/2024 | 05/01/2024 | Resource Division | 5.61 | 0 | 0 | 0
Total | [13 empty] | 55.27 | 0 | 0