## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTIPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001340/2022-2023 | 2345/W/MMD | 29/12/2022 | 11/06/2025 | GOENKA ENTERPRISE | 25.26 | 0 | 0 | 30
2 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 29/02/2024 | S.S.GHORAI | 0.45 | 0.05 | 12.09 | 100
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Material Requisition To Resource Division |  |  | RTOR000208/2022-2023 | 2466/TD | 16/01/2023 | 16/01/2023 | Resource Division | 21.59 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Crossing permission of laying HDPE pipeline along and across of NH-116 (from Mecheda bus stop to Hakola Bus stop) of Santipur Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001182/2023-2024 | 741/TD | 28/02/2024 | 19/03/2024 | DONA ASSOCIATES | 9.24 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk, Haldia Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000410/2024-2025 | 833/HESD | 28/08/2024 | 12/09/2024 | S.S.GHORAI | 2.13 | 0 | 0 | 70
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 27/08/2024 | S.S.GHORAI | 0.45 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Santipur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2024-2025 | 3764/TD | 10/12/2024 | 20/12/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 117/TD | 05/01/2024 | 05/01/2024 | Resource Division | 14.4 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Santipur W/S scheme H/W Site Application No.-2004562690 Ref.-204191008 |  |  | BILL/03464/2023-2024 | BP-2023-24-589 | 02/02/2024 | 02/02/2024 | WBSEDCL | 10.61 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SANTIPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12151 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 40
Total | [13 empty] | 89.85 | 0.05 | 0.06