## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Material Requisition To Resource Division |  |  | RTOR000207/2022-2023 | 2465/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.6 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Electric Quotation for HARINAN Water Supply Scheme , (Ref. ID-204069690) |  |  | BILL/01871/2023-2024 | W/23-24/224 | 01/09/2023 | 01/09/2023 | WBSEDCL | 3.04 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Electric Quotation for HARINAN, Water Supply Scheme T/W-II , (Ref. ID-204069696) |  |  | BILL/01872/2023-2024 | W/23-24/225 | 01/09/2023 | 01/09/2023 | WBSEDCL | 3.25 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Laying Distribution system of pipe line and its allied works for Harinan water supply scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000700/2023-2024 | 2736/TD | 01/11/2023 | 01/01/2026 | TAPAS SANTRA | 85.07 | 76.45 | 89.86 | 75
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 29/02/2024 | S.S.GHORAI | 0.45 | 0.05 | 12.09 | 100
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARINAN PWSS and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001333/2022-2023 | 2338/W/MMD | 29/12/2022 | 27/06/2023 | DEY ENTERPRISE | 23.7 | 22.63 | 95.51 | 85
7 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 90/TD | 05/01/2024 | 05/01/2024 | Resource Division | 12.69 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | HARINAN PWSS & ADJOINING MOUJAS | SM/12152 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 27/08/2024 | S.S.GHORAI | 0.45 | 0 | 0 | 100
Total | [13 empty] | 147.23 | 99.13 | 67.33