## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001350/2022-2023 | 2361/W/MMD | 31/12/2022 | 29/06/2023 | WEST BENGAL ENGINEERING CO. | 23.67 | 23.13 | 97.72 | 100
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2305 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of MIRJAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000225/2023-2024 | 456/TD | 04/05/2023 | 18/04/2026 | TAPAS SANTRA | 719.36 | 478.77 | 66.55 | 66
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Construction boundary wall & Accommodate FHTC (200 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000444/2023-2024 | 1452/TD | 13/07/2023 | 12/08/2023 | HYDROTECH ASSOCIATES | 13.65 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Material Requisition To Resource Division |  |  | RTOR000193/2022-2023 | 2380/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.37 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-II, (Ref. ID-204090824) |  |  | BILL/02893/2023-2024 | BP-2023-24-316 | 01/11/2023 | 01/11/2023 | WBSEDCL | 1.14 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-I, (Ref. ID-204086227) |  |  | BILL/02892/2023-2024 | BP-2023-24-313 | 01/11/2023 | 01/11/2023 | WBSEDCL | 3.78 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | MIRJAPUR AND ADJOINING MOUJAS PWSS | SM/12153 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 87/TD | 05/01/2024 | 05/01/2024 | Resource Division | 14.2 | 0 | 0 | 0
Total | [13 empty] | 795.17 | 501.9 | 63.12