## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA RADHAPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001334/2022-2023 | 2339/W/MMD | 29/12/2022 | 27/06/2023 | MAHADEV ENTERPRISE | 23.63 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1870 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PURBA RADHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000406/2023-2024 | 1090/TD | 08/06/2023 | 28/12/2025 | DAS ENTERPRISE | 595.42 | 251.29 | 42.2 | 65
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Wideing of approach road of Head work Site of Purba Radhapur PWSS under Bhagabanpur-I. Block under Contai Sub-Division of Tamluk Division , P.H.E. Dte Dist- Purba Medinipur | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000739/2023-2024 | 3066/TD | 30/11/2023 | 20/12/2023 | PARTHA CONSTRUCTION | 3.89 | 3.64 | 93.43 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Material Requisition To Resource Division |  |  | RTOR000197/2022-2023 | 2383/TD | 16/01/2023 | 16/01/2023 | Resource Division | 47.81 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 86/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.52 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Quotation Bill for New Service connection at T/W NO-II Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835536 Application type-New connection Consumer Id- 204365524 |  |  | BILL/02120/2024-2025 | C082448207124 | 02/09/2024 | 02/09/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835493 Application type-New connection Consumer Id- 204365530 |  |  | BILL/02118/2024-2025 | C082448216760 | 02/09/2024 | 02/09/2024 | WBSEDCL | 7.35 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | PURBA RADHAPUR & ADJOINING MOUZAS | SM/12154 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Purba Radhapur at Bhagwanpur - I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engiener,Junior Engineer | ORD/000585/2024-2025 | 461/TD | 04/02/2025 | 14/02/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
Total | [13 empty] | 694.8 | 254.92 | 36.69