## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOYALDA and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001319/2022-2023 | 2321/W/MMD | 29/12/2022 | 01/04/2025 | S.S.GHORAI | 22.81 | 17.99 | 78.88 | 100
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 17/01/2026 | SANKHA ENTERPRISE | 1144 | 201.16 | 17.58 | 30
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Material Requisition To Resource Division |  |  | RTOR000201/2022-2023 | 2438/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.42 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Goyalda W/S scheme, TW-I, site tarat(near swasan) application no-2004515964 id-204153046 |  |  | BILL/03149/2023-2024 | BP-2023-24-457 | 21/12/2023 | 21/12/2023 | WBSEDCL | 3.74 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Goyalda W/S scheme, TW-II, site tarat(near Tower) application no-2004515995 id-204153075 |  |  | BILL/03148/2023-2024 | BP-2023-24-456 | 21/12/2023 | 21/12/2023 | WBSEDCL | 3.23 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | GOYALDA & ADJOINING MOUZAS PWSS | SM/12155 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 1635/TD | 18/06/2025 | 18/06/2025 | Resource Division | 9.75 | 0 | 0 | 0
Total | [13 empty] | 1263.78 | 219.15 | 17.34