## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Providing drilling crew and other allied works for construction of Tube Well(250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Bijaynagar W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000108/2023-2024 | 1394/CDD | 19/09/2023 | 19/10/2023 | MENAKA ENTERPRISE | 27.2 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Material Requisition To Resource Division |  |  | RTOR000307/2022-2023 | 2964/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.56 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Contai-I, Deshpran(Contai-II), Contai-III, Bhagwanpur-I & Bhagwanpur-II ) | Assistant Engineer | Junior Engineer | ORD/001290/2023-2024 | 562/CSD | 14/03/2024 | 24/03/2024 | BISWA NIRMAN ENTERPRISE. | 0.68 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 629/W | 20/02/2024 | 20/02/2024 | Resource Division | 10.78 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Bijoynagar W/S scheme T/W-I Application.-2004537086 Ref.-204168733 |  |  | BILL/03295/2023-2024 | BP-2023-24-530 | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.08 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Bijoynagar W/S scheme T/W-II Application.-2004537378 Ref.-204168879 |  |  | BILL/03294/2023-2024 | BP-2023-24-529 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1750 nos) under JJM with allied work for BIJAYNAGAR PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000480/2023-2024 | 1553/TD | 19/07/2023 | 01/05/2025 | TARUN KOLEY | 555.04 | 265.45 | 47.83 | 70
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Bijaynagar & adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000485/2024-2025 | 3753/TD | 06/12/2024 | 25/01/2025 | BHOWMIK & SONS | 10.64 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BIJAYNAGAR & ADJOINING MOUJAS PWSS | SM/12157 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIJAYNAGAR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001320/2022-2023 | 2322/W/MMD | 29/12/2022 | 21/12/2024 | GOENKA ENTERPRISE | 22.8 | 21.04 | 92.28 | 100
Total | [13 empty] | 651.32 | 286.49 | 43.99