## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Material Requisition To Resource Division |  |  | RTOR000195/2022-2023 | 2382/TD | 16/01/2023 | 16/01/2023 | Resource Division | 23.95 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GAR BHERA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001336/2022-2023 | 2341/W/MMD | 29/12/2022 | 27/06/2023 | BHABANI PRASAD MANNA | 23.7 | 22.14 | 93.41 | 85
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 120/TD | 05/01/2024 | 05/01/2024 | Resource Division | 7.85 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Gar Bhera W/S scheme T/W-V Application No.-2004553977 Ref.-204184071 |  |  | BILL/03358/2023-2024 | BP-2023-24-573 | 18/01/2024 | 18/01/2024 | WBSEDCL | 5.53 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Garbhera W/S scheme T/W-II Application No.-2004554001 Ref.-204184072 |  |  | BILL/03359/2023-2024 | BP-2023-24-580 | 18/01/2024 | 18/01/2024 | WBSEDCL | 7.59 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | GAR BHERA & ADJOINING MOUZAS | SM/12159 | New | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1594 nos) under JJM with allied work of GARBERHA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000074/2023-2024 | 131/TD | 10/04/2023 | 31/05/2025 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 454.99 | 308.41 | 67.78 | 75
Total | [13 empty] | 523.62 | 330.55 | 63.13