## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Material Requisition To Resource Division |  |  | RTOR000238/2022-2023 | 2729/TD | 06/02/2023 | 06/02/2023 | Resource Division | 19.06 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ABAS BERYA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001341/2022-2023 | 2346/W/MMD | 29/12/2022 | 27/06/2023 | EASTERN INDIA SALES & SERVICE | 25.25 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 75/TD | 05/01/2024 | 05/01/2024 | Resource Division | 9.71 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Quotation Bill for New Service connection at T/W NO-II Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004940081/QUOT/03 DT. 24-10-2024 Application NO- 2004940081 Application type-New connection CONSUMER ID: 204426079 |  |  | BILL/03001/2024-2025 | C112423541900 | 19/11/2024 | 19/11/2024 | WBSEDCL | 14.89 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Quotation Bill for New Service connection at T/W NO-I Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818449/QUOT/03 DT. 12-07-2024 Application NO- 2004818449 Application type-New connection Consumer Id- 204355505 |  |  | BILL/01889/2024-2025 | BP-2024-25-552 | 08/08/2024 | 08/08/2024 | WBSEDCL | 3.11 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Sinking tube well ,Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1418 nos), Including 2 years of Operation & Maintenance under JJM with allied work of Abas Berya PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000425/2023-2024 | 1414/TD | 12/07/2023 | 08/01/2024 | SUDHAMAY MAJUMDAR | 462.29 | 101.03 | 21.85 | 45
7 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | ABAS BERYA & ADJOINING MOUZAS | SM/12162 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Abas Beriya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000450/2024-2025 | 3479/TD | 06/11/2024 | 16/11/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 535.27 | 101.03 | 18.87