## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 351/TD | 26/04/2023 | 26/04/2023 | Resource Division | 14.49 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 1663/TD | 29/04/2024 | 29/04/2024 | Resource Division | 16.25 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Satsatamal W/S scheme PH-II Application no.-2004544493 Ref.-204176804 |  |  | BILL/03456/2023-2024 | BP-2023-24-578 | 18/01/2024 | 18/01/2024 | WBSEDCL | 9.26 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Satsatamal W/S scheme PH-I Application.-2004536916 Ref.-204169242 |  |  | BILL/03296/2023-2024 | BP-2023-24-533 | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATSATMAL and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001364/2022-2023 | 2375/W/MMD | 31/12/2022 | 31/05/2025 | AHALYA ENGINEERING WORKS | 25.25 | 18.31 | 72.49 | 90
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | SATSATMAL & ADJOINING MOUJAS PWSS | SM/12163 | New | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 30/05/2026 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 306.53 | 25.24 | 60
Total | [13 empty] | 1283.81 | 324.84 | 25.3