## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | PATNA & ADJOINING MOUZAS | SM/12164 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Patna W/S Scheme (T/W-I) ,Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000104/2023-2024 | 852/CDD | 10/07/2023 | 09/08/2023 | C.M. ENTERPRISE | 15.47 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | PATNA & ADJOINING MOUZAS | SM/12164 | New | Material Requisition To Resource Division |  |  | RTOR000229/2022-2023 | 2710/TD | 06/02/2023 | 06/02/2023 | Resource Division | 6.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | PATNA & ADJOINING MOUZAS | SM/12164 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PATNA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001372/2022-2023 | 2383/W/MMD | 31/12/2022 | 29/06/2023 | P.K.ENGINEERING | 27.7 | 19.5 | 70.4 | 60
4 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | PATNA & ADJOINING MOUZAS | SM/12164 | New | Material Requisition To Resource Division |  |  | RTOR000079/2024-2025 | 2971/TD | 12/09/2024 | 12/09/2024 | Resource Division | 18.05 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | PATNA & ADJOINING MOUZAS | SM/12164 | New | Quotation for new service connection at Patna w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640160, Ref ID - 204244152) |  |  | BILL/04491/2023-2024 | BP-2023-24-855 | 16/03/2024 | 16/03/2024 | WBSEDCL | 7.46 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | PATNA & ADJOINING MOUZAS | SM/12164 | New | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 01/07/2025 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 437.25 | 25.76 | 60
7 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | PATNA & ADJOINING MOUZAS | SM/12164 | New | Instalation of display Board at different work site of Patna, Jahanabad & its adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000567/2024-2025 | 2443/CSD | 22/10/2024 | 29/10/2024 | M/S. NEW DINDA ENTERPRISE | 0.42 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | PATNA & ADJOINING MOUZAS | SM/12164 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at PATNA PWSS at Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000376/2025-2026 | 1375/CSD | 03/06/2025 | 18/06/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
Total | [13 empty] | 1774.12 | 456.75 | 25.75