## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 2387/TD | 16/01/2023 | 16/01/2023 | Resource Division | 23.22 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer |  | ORD/000845/2022-2023 | 00/TD | 10/03/2023 | 06/09/2023 | SRIMANTA KUMAR MAITY | 0 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Laying distribution pipe line & Accommodate FHTC ( 480 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000846/2022-2023 | 3189/TD | 10/03/2023 | 01/12/2025 | SRIMANTA KUMAR MAITY | 67.29 | 0 | 0 | 50
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Laying distribution pipe line & Accommodate FHTC (83 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000847/2022-2023 | 3190/TD | 10/03/2023 | 31/03/2026 | KAMAL KUMAR BERA | 19.35 | 0 | 0 | 75
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Laying of Distribution pipe line by HDPE pipes with allied works of URURI- PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(PART-E) | Assistant Engineer | Junior Engineer | ORD/001147/2023-2024 | 567/TD | 15/02/2024 | 31/03/2026 | KAMAL KUMAR BERA | 5.66 | 0 | 0 | 80
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Instalation of display Board at different work site of Ururi, Garabar, Itaberia & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001168/2023-2024 | 2328/CSD | 29/12/2023 | 08/01/2024 | KAMAL KUMAR BERA | 0.62 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 628/W | 20/02/2024 | 20/02/2024 | Resource Division | 13.76 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Quotation Bill for New Service connection at T/W NO-II Under URURI W/S Scheme under MMD,PHE,Dte. Ref. Quotation no- 2004558742/Quot/03 dt. 10- Jan-24 quotation Due date- 09-Jan-25 Application NO- 2004558742 Application type-New connection Reference Id- 204188975 |  |  | BILL/03657/2023-2024 | BP-2023-24-676 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Quotation Bill for New Service connection at T/W NO-II Of URURI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004570649/QUOT/03 DT. 22-01-2024 Application NO- 2004570649 Application type-New connection Consumer Id- 204198017 |  |  | BILL/01133/2024-2025 | BP-2024-25-249 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.76 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000853/2023-2024 | 139/TD | 05/01/2024 | 30/04/2025 | SRIMANTA KUMAR MAITY | 242.35 | 0 | 0 | 45
12 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | URURI AND ADJOINING MOUJAS PWSS | SM/12166 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 21721.6 | 0 | 0