## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Material Requisition To Resource Division |  |  | RTOR000306/2022-2023 | 2963/TD | 27/02/2023 | 27/02/2023 | Resource Division | 35.87 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (1165 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 530/TD | 12/05/2023 | 31/07/2023 | SWARUPANANDA DAS | 240.51 | 0 | 0 | 70
3 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 230 Mtrs. Depth) by utilizing Departmental Machineries for Kayemgeria W/S Scheme (T/W-I & II), Bhagawanpur-II Block underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000105/2023-2024 | 1393/CDD | 19/09/2023 | 16/04/2024 | PADMA ENGINEERING & CO. | 27.2 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 627/W | 20/02/2024 | 20/02/2024 | Resource Division | 12.66 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Quotation Bill for New Service connection at T/W NO-I Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004570684/QUOT/03 DT. 22-01-2024 Application NO- 2004570684 Application type-New connection Consumer Id- 204198020 |  |  | BILL/04389/2023-2024 | BP-2023-24-819 | 13/03/2024 | 13/03/2024 | WBSEDCL | 4.4 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Quotation Bill for New Service connection at T/W NO-II Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558744/QUOT/03 DT. 10-01-2024 Application NO- 2004558744 Application type-New connection Consumer Id- 204188974 |  |  | BILL/04393/2023-2024 | BP-2023-24-818 | 13/03/2024 | 13/03/2024 | WBSEDCL | 4.19 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAYEMGERYA and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001321/2022-2023 | 2323/W/MMD | 29/12/2022 | 10/12/2025 | MAA TARA ENTERPRISE | 22.75 | 0 | 0 | 45
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | KAYEMGERYA AND ADJOINING MOUJAS PWSS | SM/12167 | New | Laying distribution pipe line & Accommodate FHTC ( 325nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - C) | Assistant Engineer | Junior Engineer | ORD/000905/2022-2023 | 3460/TD | 27/03/2023 | 19/12/2024 | GIRI ENTERPRISE | 37.99 | 0 | 0 | 45
Total | [13 empty] | 385.57 | 0 | 0