## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 2453/TD | 16/01/2023 | 16/01/2023 | Resource Division | 37.57 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kekai PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000157/2024-2025 | 2069/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Material Requisition To Resource Division |  |  | RTOR000047/2024-2025 | 1654/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.04 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Quotation Bill for New Service connection at T/W NO-II Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657831/QUOT/03/1513 DT. 28-03-2024 Application NO- 2004657831 Application type-New connection Consumer Id- 204257680 |  |  | BILL/00260/2024-2025 | BP-2024-25-30 | 15/04/2024 | 15/04/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Bill or Damage of road flank / hard shoulder due to cutting of hard shoulder and road flank on Egra-Bajkul Road from 5.30 Km. To 7.00 Km. For laying water pipe line of Kekai PWSS. |  |  | BILL/00988/2024-2025 | BP-2024-25-492 | 01/10/2024 | 01/10/2024 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.03 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Charges for WBSEDCL for Shifting of Rail Pole of 33 KV OH Line at Kekai, Junpukur under Tamluk Division, PHE Dte. |  |  | BILL/01216/2024-2025 | BP-2024-25-633 | 30/11/2024 | 30/11/2024 | WBSEDCL | 0.87 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Quotation Bill for New Service connection at T/W NO-I Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760163/QUOT/03 DT. 04-06-2024 Application NO- 2004760163 Application type-New connection Consumer Id- 204322029 |  |  | BILL/01231/2024-2025 | BP-2024-25-287 | 18/06/2024 | 18/06/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 136.54 | 0.7 | 51
9 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KEKAI & ADJOINING MOUJAS PWSS | SM/12168 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KEKAI and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001366/2022-2023 | 2377/W/MMD | 31/12/2022 | 18/06/2025 | GHOSH ENGINEERING SYNDICATE | 25.24 | 5.85 | 23.17 | 51
Total | [13 empty] | 19594.5 | 143.34 | 0.73