## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Material Requisition To Resource Division |  |  | RTOR000298/2022-2023 | 2962/TD | 27/02/2023 | 27/02/2023 | Resource Division | 65.74 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Laying distribution pipe line & Accommodate FHTC (370 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000447/2023-2024 | 1466/TD | 13/07/2023 | 01/10/2024 | R CONSTRUCTION | 69.75 | 0 | 0 | 60
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 626/W | 20/02/2024 | 20/02/2024 | Resource Division | 15.22 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Quotation Bill for New Service connection at T/W NO-II Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601928/QUOT/03 DT. 15-02-2024 Application NO- 2004601928 Application type-New connection Reference Id- 204217837 |  |  | BILL/04266/2023-2024 | BP-2023-24-794 | 06/03/2024 | 06/03/2024 | WBSEDCL | 4 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Additional Quotation Bill cost for Diversion of route due to RAW at the PHE Site-BAHADURPUR W/S SCHEME,T/W NO-II, MADHABPUR Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/260 DT. 17-05-2024 Application NO- 100000108126 DT. 17-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300546 |  |  | BILL/01144/2024-2025 | BP-2024-25-242 | 06/06/2024 | 06/06/2024 | WBSEDCL | 1.41 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Quotation Bill for New Service connection at T/W NO-I Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004768458/QUOT/03 DT. 11-06-2024 Application NO- 2004768458 Application type-New connection Consumer Id- 204327319 |  |  | BILL/00596/2024-2025 | BP-2024-25-294 | 29/07/2024 | 29/07/2024 | WBSEDCL | 10.84 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 1049/TD | 07/06/2023 | 01/05/2025 | TARUN KOLEY | 266.16 | 0 | 0 | 65
8 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Laying distribution pipe line & Accommodate FHTC ( 700nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer | Junior Engineer | ORD/000270/2023-2024 | 531/TD | 12/05/2023 | 31/10/2025 | M/S SREE DURGA ENTERPRISE | 138.34 | 0 | 0 | 53
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Laying of Distribution pipe line by HDPE pipes with allied works for Left Out Area due to Revised Drawing of BAHADURPUR PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000709/2023-2024 | 2875/TD | 17/11/2023 | 28/09/2025 | M/S SREE DURGA ENTERPRISE | 33.75 | 0 | 0 | 97
11 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | BAHADURPUR AND ADJOINING MOUJAS PWSS | SM/12169 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 21947.17 | 0 | 0