## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Material Requisition To Resource Division |  |  | RTOR000147/2022-2023 | 2452/TD | 16/01/2023 | 16/01/2023 | Resource Division | 24.44 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Panchet PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000192/2024-2025 | 2202/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Material Requisition To Resource Division |  |  | RTOR000053/2024-2025 | 1662/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.82 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Quotation Bill for New Service connection at T/W NO-II Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004626644/QUOT/03 DT. 01-03-2024 Application NO- 2004626644 Application type-New connection Consumer Id- 204234144 |  |  | BILL/04391/2023-2024 | BP-2023-24-820 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.99 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Quotation Bill for New Service connection at T/W NO-I Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649232/QUOT/03 DT. 20-03-2024 Application NO- 2004649232 Application type-New connection Consumer Id- 204250589 |  |  | BILL/00007/2024-2025 | BP-2024-25-3 | 04/04/2024 | 04/04/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | PANCHET AND ADJOINING MOUJAS PWSS | SM/12170 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PANCHET and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001367/2022-2023 | 2378/W/MMD | 31/12/2022 | 18/06/2025 | GHOSH ENGINEERING SYNDICATE | 25.24 | 0 | 0 | 45
Total | [13 empty] | 73.43 | 0 | 0