## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Material Requisition To Resource Division |  |  | RTOR000296/2022-2023 | 2961/TD | 27/02/2023 | 27/02/2023 | Resource Division | 33.37 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Laying Distribution pipe line & Accommodate FHTC (330 nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000910/2022-2023 | 3465/TD | 27/03/2023 | 11/05/2023 | SUBHENDU HAZRA | 76.59 | 47.28 | 61.73 | 60
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (511 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000391/2023-2024 | 1050/TD | 07/06/2023 | 04/12/2023 | TARUN KOLEY | 222.99 | 45.72 | 20.5 | 22
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 625/W | 20/02/2024 | 20/02/2024 | Resource Division | 12.23 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Laying distribution pipe line & Accommodate FHTC ( 180nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer | Junior Engineer | ORD/000911/2022-2023 | 3466/TD | 27/03/2023 | 23/01/2024 | SUBRATA KUMAR BERA | 28.31 | 16.28 | 57.52 | 60
6 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (850 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 536/TD | 12/05/2023 | 31/07/2023 | GIRI CONSTRUCTION | 191.14 | 78.24 | 40.93 | 42
8 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 10/09/2024 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
10 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | MANIKJOR AND ADJOINING MOUJAS PWSS | SM/12171 | New | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Manikjore PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte |  |  | ORD/000580/2024-2025 | 458/TD | 04/02/2025 | 16/03/2025 | B. K. ENTERPRISE | 26.18 | 0 | 0 | 0
Total | [13 empty] | 21943.2 | 187.52 | 0.85