## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | SM/12172 | New | Material Requisition To Resource Division |  |  | RTOR000148/2022-2023 | 2451/TD | 16/01/2023 | 16/01/2023 | Resource Division | 32.56 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | SM/12172 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASBAPATASHPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001353/2022-2023 | 2364/W/MMD | 31/12/2022 | 29/06/2023 | JAL PRAVAHIKA PVT. LTD. | 23.44 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | SM/12172 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kasba Patashpur PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000153/2024-2025 | 2064/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | SM/12172 | New | Material Requisition To Resource Division |  |  | RTOR000045/2024-2025 | 1652/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.55 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KASBAPATASHPUR & ADJOINING MOUJAS PWSS | SM/12172 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 13.52 | 0.07 | 51
Total | [13 empty] | 19576.21 | 14.47 | 0.07