## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Material Requisition To Resource Division |  |  | RTOR000294/2022-2023 | 2960/TD | 27/02/2023 | 27/02/2023 | Resource Division | 33.17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Laying distribution pipe line, Pump House & Accommodate FHTC (315 nos), Boundary Wall under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000065/2023-2024 | 135/TD | 10/04/2023 | 25/05/2023 | SOUMYA ENTERPRISE | 53.18 | 0 | 0 | 67
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Instalation of display Board at different work site of Panch Bajari, Manikjor, Bahadurpur, Kayemgerya, & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001166/2023-2024 | 2327/CSD | 29/12/2023 | 13/01/2024 | M/S. NEW DINDA ENTERPRISE | 0.83 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 624/W | 20/02/2024 | 20/02/2024 | Resource Division | 6.25 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Quotation Bill for New Service connection at T/W NO-I Of Panchbajari W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601878/QUOT/03 DT. 15-02-2024 Quotation due date-14.02.2025 Application NO- 2004601878 Application type-New connection Reference Id- 204217833 |  |  | BILL/04263/2023-2024 | BP-2023-24-793 | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.1 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Laying distribution pipe line,Pump House, Accommodate FHTC & Boundary Wall (400 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000064/2023-2024 | 134/TD | 10/04/2023 | 29/03/2025 | JAI BHARAT COMMERCIAL CORPORATION | 78.91 | 0 | 0 | 65
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Laying distribution pipe line & Accommodate FHTC (100 nos) under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000066/2023-2024 | 136/TD | 10/04/2023 | 14/05/2025 | SUDIP MANNA | 19.43 | 0 | 0 | 60
8 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PANCH BAJARI & ADJOINING MOUJAS PWSS | SM/12173 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 21537.83 | 0 | 0