## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Material Requisition To Resource Division |  |  | RTOR000339/2022-2023 | 2976/TD | 27/02/2023 | 27/02/2023 | Resource Division | 32.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Material Requisition To Resource Division |  |  | RTOR000066/2024-2025 | 2946/TD | 12/09/2024 | 12/09/2024 | Resource Division | 11.38 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Ajaya W/S scheme T/W -II Application No.-2004565730 Ref.-204193622 |  |  | BILL/03476/2023-2024 | BP-2023-24-592 | 02/02/2024 | 02/02/2024 | WBSEDCL | 8.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Ajaya W/S scheme T/W -I Application No.-2004565721 Ref.-204193605 |  |  | BILL/03475/2023-2024 | BP-2023-24-593 | 02/02/2024 | 02/02/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | AJAYA & ADJOINING MOUJAS PWSS | SM/12174 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJAYA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002290/2022-2023 | 2384/W/MMD | 31/12/2022 | 29/06/2023 | P.K.ENGINEERING | 27.7 | 0 | 0 | 45
Total | [13 empty] | 21422.89 | 0 | 0