## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 2450/TD | 16/01/2023 | 16/01/2023 | Resource Division | 31.66 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharat Katbar PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000188/2024-2025 | 2198/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 1656/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.67 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Quotation Bill for New Service connection at T/W NO-I Of KHARAT KOTBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760152/QUOT/03 DT. 04-06-2024 Application NO- 2004760152 Application type-New connection Consumer Id- 204322027 |  |  | BILL/01276/2024-2025 | BP-2024-25-319 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Quotation Bill for New Service connection at T/W NO-II Of KHARATKOTBAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811790/QUOT/03 DT. 11-07-2024 Application NO- 2004811790 Application type-New connection Consumer Id- 204351927 |  |  | BILL/01977/2024-2025 | BP-2024-25-565 | 14/08/2024 | 14/08/2024 | WBSEDCL | 5.76 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARAT KATBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001370/2022-2023 | 2381/W/MMD | 31/12/2022 | 07/04/2028 | ECO ENTERPRISE | 25.26 | 0 | 0 | 85
7 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
8 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KHARAT KATBAR & ADJOINING MOUJAS PWSS | SM/12175 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
Total | [13 empty] | 19588.98 | 0 | 0