## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RUKMINIPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Junior Engineer, Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001354/2022-2023 | 2365/W/MMD | 31/12/2022 | 31/08/2025 | ABHIJIT BASU | 23.69 | 14.81 | 62.5 | 80
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1588 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Rukminipur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000232/2023-2024 | 460/TD | 04/05/2023 | 28/09/2026 | FIROZ KHAN | 483.49 | 204.95 | 42.39 | 70
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Material Requisition To Resource Division |  |  | RTOR000253/2022-2023 | 2716/TD | 06/02/2023 | 06/02/2023 | Resource Division | 34.45 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Quotation Bill for New Service connection at T/W NO-I Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004701293/QUOT/03/98 DT. 25-04-2024 Application NO- 2004701293 Application type-New connection Consumer Id- 204287569 |  |  | BILL/00856/2024-2025 | BP-2024-25-162 | 15/05/2024 | 15/05/2024 | WBSEDCL | 3.52 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Quotation Bill for New Service connection at T/W NO-II Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792717/QUOT/03/381 DT. 02/07/2024 Application NO- 2004792717 Application type-New connection Consumer Id- 204345882 |  |  | BILL/01699/2024-2025 | BP-2024-25-493 | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.04 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RUKMINIPUR AND ADJOINING MOUJAS PWSS | SM/12176 | New | Material Requisition To Resource Division |  |  | RTOR000029/2025-2026 | 2086/TD | 12/08/2025 | 12/08/2025 | Resource Division | 9.78 | 0 | 0 | 0
Total | [13 empty] | 558.98 | 219.76 | 39.31