## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000289/2022-2023 | 2645/TD | 02/02/2023 | 02/02/2023 | Resource Division | 16.37 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000485/2022-2023 | 1890/TD | 24/11/2022 | 23/01/2023 | H. SAMANTA | 123.68 | 64.87 | 52.46 | 53
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block. | SM/12177 | Retrofitting | Construction of approach road at H/W site & 2nd T/W site of Sarrang Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000587/2024-2025 | 209/TD | 15/01/2025 | 14/02/2025 | ASEMA ENTERPRISE | 1.95 | 0 | 0 | 0
Total | [13 empty] | 141.99 | 64.87 | 45.69