## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Renovation work of Spiral stair and related works for R.C.C. Over Head Reservoir of capacity 60000 Gallons at Keshurkunda mouza within Contai S.A. Zone-II W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur.( 2nd Part) | Assistant Engineer |  | ORD/000255/2021-2022 | 497 / CSD | 18/11/2021 | 09/12/2021 | SRIMANTA KUMAR MAITY | 2.06 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000449/2021-2022 | 1684/TD | 28/01/2022 | 17/02/2022 | ROY CHOWDHURY ASSOCIATES | 4.86 | 4.85 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 01/11/2022 | B. K. ENTERPRISE | 72.46 | 15.29 | 21.11 | 63
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1663/TD | 03/11/2022 | 03/11/2022 | Resource Division | 315.36 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 612/TD | 17/05/2023 | 17/05/2023 | Resource Division | 37.05 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai-I & III Dev. Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 1972/TD | 01/12/2022 | 01/08/2025 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 938.66 | 272.74 | 29.06 | 45
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II) | SM/12268 | Augmentation | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division P.H.E. DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 1906/TD | 07/06/2024 | 03/06/2025 | SK. NUR ISLAM | 45.39 | 0 | 0 | 35
Total | [13 empty] | 1415.83 | 292.89 | 20.69