## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 614/TD | 17/05/2023 | 17/05/2023 | Resource Division | 30.14 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1664/TD | 03/11/2022 | 03/11/2022 | Resource Division | 325.57 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Contai S.A Zone -III W/S scheme PH-II Application no.-2004474775 ref.-204117777 |  |  | BILL/03195/2023-2024 |  | 15/12/2023 | 15/12/2023 | WBSEDCL | 4.72 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4893 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000513/2022-2023 | 2063/TD | 09/12/2022 | 29/03/2025 | TARUN KOLEY | 1059.62 | 0 | 0 | 80
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 2340/TD | 10/01/2023 | 19/02/2023 | M/S SYCHROTECH INDUSTRY | 57.41 | 0 | 0 | 60
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Pump House and Rising main, under Augmentation of Contai Saline Area Zone-III (Phase-B) PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2023-2024 | 2199/TD | 01/09/2023 | 11/10/2023 | S B ENTERPRISE | 25.16 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001918/2022-2023 | 822/W/MMD | 24/03/2023 | 13/03/2025 | P.K.ENGINEERING | 40.78 | 0 | 0 | 80
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Supply of documents for way leave permission of Railway Track Between NACHINDA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I (Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (TD-46/09-10) | Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 141/CSD | 16/01/2025 | 05/02/2025 | SUBHENDU HAZRA | 1.16 | 0 | 0 | 0
Total | [13 empty] | 1544.55 | 0 | 0