## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4893 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000513/2022-2023 | 2063/TD | 09/12/2022 | 29/03/2025 | TARUN KOLEY | 1059.62 | 828.04 | 78.15 | 80
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. |  |  | ORD/000014/2022-2023 | 48/TD | 05/04/2022 | 25/04/2022 | INDRANIL DUTTA & ASSOCIATES | 8.67 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. |  |  | ORD/000013/2022-2023 | 47/TD | 05/04/2022 | 25/04/2022 | INDRANIL DUTTA & ASSOCIATES | 5.82 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 1664/TD | 03/11/2022 | 03/11/2022 | Resource Division | 325.57 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 2340/TD | 10/01/2023 | 19/02/2023 | M/S SYCHROTECH INDUSTRY | 57.41 | 30.27 | 52.73 | 60
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001918/2022-2023 | 822/W/MMD | 24/03/2023 | 13/03/2025 | P.K.ENGINEERING | 40.78 | 28.91 | 70.91 | 80
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Pump House and Rising main, under Augmentation of Contai Saline Area Zone-III (Phase-B) PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2023-2024 | 2199/TD | 01/09/2023 | 11/10/2023 | S B ENTERPRISE | 25.16 | 19.96 | 79.34 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 614/TD | 17/05/2023 | 17/05/2023 | Resource Division | 30.14 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Contai S.A Zone -III W/S scheme PH-II Application no.-2004474775 ref.-204117777 |  |  | BILL/03195/2023-2024 |  | 15/12/2023 | 15/12/2023 | WBSEDCL | 4.72 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Renovation work of Spiral Staircase, Support UC Post For Raising Main line , Shutter Gate of Office Cum Godown at Contai Saline Area Zone -III ( Phase-A) W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000570/2024-2025 | 2447/CSD | 22/10/2024 | 12/11/2024 | M/S SREE DURGA ENTERPRISE | 0.96 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Supply of documents for way leave permission of Railway Track Between NACHINDA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I (Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (TD-46/09-10) | Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 141/CSD | 16/01/2025 | 05/02/2025 | SUBHENDU HAZRA | 1.16 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Laying of Damaged HDPE Pipe line of 180 mm dia with allied works under Augmentation of Contai Saline area Zone-III( Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(N.P.-1074 -1084 Part) | Assistant Engineer | Junior Engineer | ORD/000358/2025-2026 | 1342/CSD | 02/06/2025 | 23/06/2025 | JASODA ENTERPRISE | 0.88 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Installation of display Board of Contai Saline Area Zone III (Zone-A) Augmentation PWSS at 4 nos. TW Site, Contai Saline Area Zone III (Zone-B) Augmentation PWSS at 1 no TW site in Contai-I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipurDistrict. | Assistant Engineer | Junior Engineer | ORD/000286/2025-2026 | 1587/CSD | 19/06/2025 | 26/06/2025 | M/S SREE DURGA ENTERPRISE | 0.83 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Installation of display Board of Contai State Welfare Home PWSS at 1 nos TW site , Contai Municipalty PWSS at 1 nos TW site , Contai S.A. ZONE - III (Ghatua store ) PWSS at 1 nos TW site in Contai - I Block for JJM works for Open Land within Contai Sub-Division under Tamluk Division, PHE Dte. PurbaMedinipur District. | Assistant Engineer | Junior Engineer | ORD/000301/2025-2026 | 1600/CSD | 19/06/2025 | 26/06/2025 | BISWA NIRMAN ENTERPRISE. | 0.5 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/12279 | Augmentation | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of CONTAI S.A.REJ.(PHASE-B) W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2005120731/QUOT/03 DT. 07-03-2025 Application NO- 2005120731 Application type-New connection Consumer Id- 204554509 |  |  | BILL/04973/2024-2025 |  | 20/03/2025 | 20/03/2025 | WBSEDCL | 3.26 | 0 | 0 | 0
Total | [13 empty] | 1626.33 | 907.19 | 55.78