## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Material Requisition To Resource Division |  |  | RTOR000332/2022-2023 | 2983/TD | 27/02/2023 | 27/02/2023 | Resource Division | 12.88 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000897/2022-2023 | 3347/TD | 22/03/2023 | 01/05/2023 | PRANTIK DRILLING AGENCY | 61.77 | 0 | 0 | 50
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000630/2023-2024 | 2438/TD | 19/09/2023 | 17/03/2024 | ANUSKA ENTERPRISE | 165.66 | 0 | 0 | 30
4 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAYACHAR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001397/2022-2023 | 2408/W/MMD | 31/12/2022 | 21/12/2024 | S.G.ENTERPRISE | 21.6 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) [Chaitanyapur Zone-I PWSS, Dwariberia PWSS, Natshal Lakshya Zone-I PWSS & Mayachar PWSS] | Assistant Engineer | Junior Engineer | ORD/000831/2023-2024 | 619/HSD, | 21/12/2023 | 28/12/2023 | SANTANU PATTANAYAK | 0.83 | 0 | 0 | 100
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Mayachar PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000151/2024-2025 | 2062/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 135/TD | 05/01/2024 | 05/01/2024 | Resource Division | 8.04 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Quotation for new service connection at Mayachar w/s scheme PH I in the district of Purba Medinipur (Application no 1007526112, Ref ID 106467554) |  |  | BILL/03781/2023-2024 | BP-2023-24-711 | 20/02/2024 | 20/02/2024 | WBSEDCL | 3.89 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MAYACHAR AND ADJOINING MOUJAS PWSS | SM/12281 | New | Quotation for new service connection at Mayachar w/s scheme PH II in the district of Purba Medinipur (Application no 1007525986, Ref ID 106467535) |  |  | BILL/03780/2023-2024 | BP-2023-24-712 | 20/02/2024 | 20/02/2024 | WBSEDCL | 6.18 | 0 | 0 | 0
Total | [13 empty] | 281.82 | 0 | 0