## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAKRAMPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001404/2022-2023 | 2415/W/MMD | 31/12/2022 | 31/05/2025 | RITESH ENTERPRISE | 22.79 | 0 | 0 | 50
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 75.02 | 0.38 | 51
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 2440/TD | 16/01/2023 | 16/01/2023 | Resource Division | 30.48 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Quotation Bill for New Service connection at T/W NO-I Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004707237/QUOT/03 DT. 29-04-2024 Application NO- 2004707237 MEMO NO: AMR/PHE/90 DT.29/04/2024 Application type-New connection Consumer Id- 204291521 |  |  | BILL/00855/2024-2025 | BP-2024-25-163 | 15/05/2024 | 15/05/2024 | WBSEDCL | 5.32 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Quotation Bill for New Service connection at T/W NO-II Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004944304/QUOT/03 DT. 25-10-2024 Application NO- 2004944304 Application type-New connection Consumer Id- 204428639 |  |  | BILL/03005/2024-2025 | C112423561463 | 19/11/2024 | 19/11/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | MAKRAMPUR AND ADJOINING MOUJAS PWSS | SM/12282 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 1633/TD | 18/06/2025 | 18/06/2025 | Resource Division | 8.76 | 0 | 0 | 0
Total | [13 empty] | 19578.23 | 75.02 | 0.38