## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALADIHA AND ADJOINING MOUJAS PWSS | SM/12283 | New | Material Requisition To Resource Division |  |  | RTOR000258/2022-2023 | 2705/TD | 06/02/2023 | 06/02/2023 | Resource Division | 51.54 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | TALADIHA AND ADJOINING MOUJAS PWSS | SM/12283 | New | Sinking Tube well,Pump House , Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1324 nos), Including 2 years of operation maintance under JJM with allied work for Taladiha PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2023-2024 | 1093/TD | 08/06/2023 | 29/04/2026 | SUJATA CONSTRUCTION | 373.7 | 66.61 | 17.83 | 21
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TALADIHA AND ADJOINING MOUJAS PWSS | SM/12283 | New | Quotation Bill for New Service connection at T/W NO-II Of TALADIHA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004969351/QUOT/03 DT. 18-11-2024 MEMO NO: AMR/PHE/512 DT. 18-11-2024 Application NO- 2004969351 Application type-New connection Consumer Id- 204448691 |  |  | BILL/03064/2024-2025 | C112433888301 | 27/11/2024 | 27/11/2024 | WBSEDCL | 6.1 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | TALADIHA AND ADJOINING MOUJAS PWSS | SM/12283 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALADIHA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001403/2022-2023 | 2414/W/MMD | 31/12/2022 | 07/04/2028 | ECO ENTERPRISE | 22.8 | 11.71 | 51.34 | 40
Total | [13 empty] | 454.14 | 78.32 | 17.25