## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Material Requisition To Resource Division |  |  | RTOR000251/2022-2023 | 2715/TD | 06/02/2023 | 06/02/2023 | Resource Division | 32.5 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at Tajpur PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 2072/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Quotation Bill for New Service connection at T/W NO-I Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626691/QUOT/03/1613 DT. 01/03/2024 Application NO- 2004626691 Application type-New connection Consumer Id- 204233925 |  |  | BILL/04504/2023-2024 | BP-2023-24-857 | 16/03/2024 | 16/03/2024 | WBSEDCL | 4.05 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Quotation Bill for New Service connection at T/W NO-II Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626737/QUOT/03/1611 DT. 01-03-2024 Application NO- 2004626737 Application type-New connection Consumer Id- 204233924 |  |  | BILL/04505/2023-2024 | BP-2023-24-856 | 16/03/2024 | 16/03/2024 | WBSEDCL | 4.66 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2785 nos) under JJM with allied work for Tajpur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2023-2024 | 1415/TD | 12/07/2023 | 01/04/2026 | FIROZ KHAN | 607.63 | 296.14 | 48.74 | 70
6 | PURBA MEDINIPUR | Egra-II | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Leftout pipeline & Drum Sheet Walling to accommodate FHTC under JJM of Tajpur Water Supply Scheme within Egra II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000068/2025-2026 | 1167/TD | 22/04/2025 | 01/06/2025 | R CONSTRUCTION | 103.69 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAJPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001587/2022-2023 | 470/W/MMD | 20/03/2023 | 02/04/2025 | SOUMEN ELECTRIC | 25.24 | 23.66 | 93.7 | 100
8 | PURBA MEDINIPUR | Egra-II | Tamluk Division | TAJPUR AND ADJOINING MOUJAS PWSS | SM/12284 | New | Material Requisition To Resource Division |  |  | RTOR000030/2025-2026 | 2089/TD | 12/08/2025 | 12/08/2025 | Resource Division | 17.16 | 0 | 0 | 0
Total | [13 empty] | 795.89 | 320.74 | 40.3