## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | DANGAR TULSI AND ADJOINING MOUJAS PWSS | SM/12285 | New | Material Requisition To Resource Division |  |  | RTOR000190/2022-2023 | 2441/TD | 16/01/2023 | 16/01/2023 | Resource Division | 33.17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS | SM/12285 | New | Quotation Bill for New Service connection at T/W NO-II Of DANGAR TULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004862083/QUOT/03 DT. 16-08-2024 MEMO NO: AMR/PHE/330 DT. 16-08-2024 Application NO- 2004862083 Application type-New connection Consumer Id- 204378443 |  |  | BILL/02119/2024-2025 | C082448267203 | 02/09/2024 | 02/09/2024 | WBSEDCL | 4.66 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS | SM/12285 | New | Quotation Bill for New Service connection at T/W NO-I Of DANGARTULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004706844/QUOT/03 DT. 29-04-2024 Application NO- 2004706844 MEMO NO: AMR/PHE/91 DT.29/04/2024 Application type-New connection Consumer Id- 204291543 |  |  | BILL/00854/2024-2025 | BP-2024-25-164 | 15/05/2024 | 15/05/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | DANGAR TULSI AND ADJOINING MOUJAS PWSS | SM/12285 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DANGAR TULSI and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001401/2022-2023 | 2412/W/MMD | 31/12/2022 | 31/05/2025 | SUJOY RANJAN BHOWMICK | 22.8 | 0 | 0 | 35
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | DANGAR TULSI AND ADJOINING MOUJAS PWSS | SM/12285 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
Total | [13 empty] | 19572.29 | 0 | 0