## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Central Drilling | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.44 | 0.22 | 11
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 1050 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED , Purba Medinipur ( Part - A) | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 1753/TD | 01/08/2023 | 01/12/2025 | SUSIL KUMAR HAZRA | 254.73 | 77.56 | 30.45 | 32
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (123 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 3554/TD | 29/03/2023 | 21/08/2025 | SUBRATA KUMAR BERA | 39.9 | 31.5 | 78.95 | 100
4 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (42 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-D) | Assistant Engineer | Junior Engineer | ORD/000918/2022-2023 | 3555/TD | 29/03/2023 | 03/09/2025 | DEBABRATA DAS | 9.94 | 6.57 | 66.06 | 100
5 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC (19 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-F) | Assistant Engineer | Junior Engineer | ORD/000919/2022-2023 | 3556/TD | 29/03/2023 | 05/06/2025 | DEBABRATA DAS | 11.2 | 9.64 | 86.09 | 100
6 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, & Accommodate FHTC ( 56 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer | Junior Engineer | ORD/000334/2023-2024 | 808/TD | 30/05/2023 | 30/06/2025 | M/S. PRADIP PRADHAN | 9.31 | 5.52 | 59.29 | 100
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 700 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B) | Assistant Engineer | Junior Engineer | ORD/000283/2023-2024 | 564/TD | 12/05/2023 | 29/04/2025 | SNEHESH SEN | 199.62 | 158.45 | 79.38 | 100
8 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Material Requisition To Resource Division |  |  | RTOR000215/2022-2023 | 2693/TD | 06/02/2023 | 06/02/2023 | Resource Division | 54.53 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Canal crossing structure for Distribution pipe line with allied works of Nijmaitana & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. N.P-From 1193 towards Kathmundi 45.0M & N.P 1190 to N.P 1191 15.0 M. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 1926/TD | 07/06/2024 | 22/06/2024 | SNEHESH SEN | 4.87 | 4.03 | 82.8 | 100
10 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 134/TD | 05/01/2024 | 05/01/2024 | Resource Division | 12.26 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Quotation for new service connection at TW-II of Nijmaitana ws scheme under MMD,PHE, Dte. Ref. Application no-2004579831. Con ID-204204430. PICHABONI CCC, BLOCK-RAMNAGAR-II |  |  | BILL/03654/2023-2024 | BP-2023-24-680 | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.07 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Nij-Maitana W/S scheme T/W-I Application No.-2004550686 Ref.-204181243 |  |  | BILL/03291/2023-2024 | BP-2023-24-540 | 11/01/2024 | 11/01/2024 | WBSEDCL | 2.76 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | NIJ MAITHUNA AND ADJOINING MOUJAS PWSS | SM/12286 | New | Laying Balance distribution pipe line,with balance FHTC and allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur |  |  | ORD/000597/2024-2025 | 569/TD | 17/02/2025 | 14/03/2025 | R CONSTRUCTION | 36.35 | 0 | 0 | 0
Total | [13 empty] | 21978.3 | 339.72 | 1.55