## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEPAL and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001359/2022-2023 | 2370/W/MMD | 31/12/2022 | 29/06/2023 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 91.65 | 85
2 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 22/07/2026 | BASANTA KUMAR MAITY | 961.33 | 200.93 | 20.9 | 60
3 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Material Requisition To Resource Division |  |  | RTOR000309/2022-2023 | 2999/TD | 27/02/2023 | 27/02/2023 | Resource Division | 22.33 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Depal W/S scheme TW no.-I Ref.-204156070 Application ID-2004521731 |  |  | BILL/03155/2023-2024 | BP-2023-24-439 | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.4 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 108/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.02 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-II | Midnapore Mechanical | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | DEPAL w/s SCHEME PH -II APPLICATION nO.-2004566534 REF.-204194525 |  |  | BILL/03535/2023-2024 | BP-2023-24-612 | 07/02/2024 | 07/02/2024 | WBSEDCL | 24.63 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar-II | Tamluk Division | DEPAL AND ADJOINING MOUJAS PWSS | SM/12287 | New | Additional Quotation for Additional Service connection Charges against APP NO: 2004521731 IRO DEPAL W/S Scheme T/W no-I AT DEPAL Under Jal Jeevan Mission under MMD, PHE, Dte. Block- RAMNAGAR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No-DGA/776 DT. 05-08-2024 Application NO- 100000115575 DT. 05-08-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860310305 |  |  | BILL/00761/2024-2025 | BP-2024-25-381 | 29/08/2024 | 29/08/2024 | WBSEDCL | 11.8 | 0 | 0 | 0
Total | [13 empty] | 1060.21 | 222.66 | 21