## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | TELAMI AND ADJOINING MOUJAS PWSS | SM/12288 | New | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 2409/TD | 16/01/2023 | 16/01/2023 | Resource Division | 35.73 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS | SM/12288 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TELAMI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001344/2022-2023 | 2355/W/MMD | 31/12/2022 | 29/06/2023 | SOUMEN ELECTRIC | 21.56 | 0 | 0 | 70
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | TELAMI AND ADJOINING MOUJAS PWSS | SM/12288 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Telami PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 2073/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS | SM/12288 | New | Quotation Bill for New Service connection at T/W NO-II Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674624/QUOT/03 DT. 09-04-2024 Application NO- 2004674624 Application type-New connection Consumer Id- 204269445 |  |  | BILL/00506/2024-2025 | BP-2024-25-88 | 24/04/2024 | 24/04/2024 | WBSEDCL | 7.55 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | TELAMI AND ADJOINING MOUJAS PWSS | SM/12288 | New | Quotation Bill for New Service connection at T/W NO-I Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674680/QUOT/03 DT. 09-04-2024 Application NO- 2004674680 Application type-New connection Consumer Id- 204269489 |  |  | BILL/00508/2024-2025 | BP-2024-25-89 | 24/04/2024 | 24/04/2024 | WBSEDCL | 5.15 | 0 | 0 | 0
Total | [13 empty] | 70.94 | 0 | 0