## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Material Requisition To Resource Division |  |  | RTOR000338/2022-2023 | 2977/TD | 27/02/2023 | 27/02/2023 | Resource Division | 33.32 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANTHI BARI and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001347/2022-2023 | 2358/W/MMD | 31/12/2022 | 29/06/2023 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Material Requisition To Resource Division |  |  | RTOR000094/2024-2025 | 2962/TD | 12/09/2024 | 12/09/2024 | Resource Division | 7.86 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Quotation bill for Kanthi Bari Water supply scheme PH-II, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711606 Reference ID.-204294517 |  |  | BILL/00448/2024-2025 | BP-2024-25-169 | 10/06/2024 | 10/06/2024 | WBSEDCL | 10.12 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Quotation bill for Kanthi Bari Water supply scheme PH-I, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711599 Reference ID.-204294533 |  |  | BILL/00857/2024-2025 | BP-2024-25-161 | 15/05/2024 | 15/05/2024 | WBSEDCL | 15.76 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KANTHI BARI AND ADJOINING MOUJAS PWSS | SM/12289 | New | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1582 nos) under JJM with allied work for Kanthi Bari & its adjoining moujas PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2023-2024 | 1516/TD | 17/07/2023 | 30/03/2026 | TAPAS SANTRA | 565.57 | 349.77 | 61.84 | 70
Total | [13 empty] | 655.41 | 349.77 | 53.37